## Sheet1
Work plan for power optimization reports
1 story point = 2 hrs
No | Module | Main Task | Sub Tasks | Dev | QA | Type of the work | Start Date | End Date | Estimated Story Points | Target Release Date | Remarks
1 | Formula Service | Integrating peak of peak/ bug fixings changes to Formula Service latest version | Get KT about the change | Chiran |  | KT
|  |  | Get KT on data patching | Nadeeka |  | KT
|  |  | Studying the code functionalities |  |  | R&D
|  |  | Integrating peak off peak/ bug fixing changes |  |  | Development
|  |  | Dev testing |  |  | Dev Testing
|  |  | Test server deployment |  |  | Deployment
|  |  | QA testing |  |  | QA testing
2 | Data sync service | Integrating performance enhancment | Get KT about the change(Performance enhancement) | Nadeeka |  | KT
|  |  | Studying the code functionalities |  |  | R&D
|  |  | Integrating performance enhancment |  |  | Development
|  |  | Dev testing |  |  | Dev Testing
|  |  | Test server deployment |  |  | Deployment
|  |  | QA testing |  |  | QA testing
3 | Formula Service | Applying a mechanism to validate minus consumptions | Discuss about scenarios that produce minus consumptions | Kalhari/Lahiru/Gayashan |  | Discussion
|  |  | Discussion to finalize the mechanism to handle the scenarios that produce minus cosnumptions | Kalhari/Lahiru/Gayashan |  | Discussion
|  |  | Discussing and KT and how to apply the approach to service | Kalhari |  | KT/Discussion
|  |  | Designing the approach(flow diagrams, class diagrams) | Kalhari |  | Development
|  |  | Finalizing the design |  |  | Discussion
|  |  | Implementation |  |  | Development
Implement Unit testing
|  |  | Dev testing |  |  | Development
|  |  | Test server deployment |  |  | Deployment
|  |  | QA testing |  |  | QA testing
4 | Report Module | Implement a feature to apply function for data series for custom time ranges | Discuss about the approach | Hasintha/Kalhari |  | Discussion
|  |  | KT on how to apply the approach to code |  |  | KT/Discussion
|  |  | Designing the approach(flow diagrams, class diagrams) |  |  | Development
|  |  | Finalizing the design |  |  | Discussion
|  |  | Implementation |  |  | Development
Preparing sample json file and template
|  |  | Dev testing |  |  | Development
|  |  | Test server deployment |  |  | Deployment
|  |  | QA testing (Console App) |  |  | QA testing
5 | Reporting Service | Implement a service to generate reports periodicaly | KT on schedule service | Kalhari |  | KT/Discussion
|  |  | Studying the code functionalities |  |  | Discussion
|  |  | Integrating schedule service report project and other projects to solution of API |  |  | Development
|  |  | Resolving issues during code compiling |  |  | Development
|  |  | Modifying code for the changes |  |  | Development
|  |  | Preparing template for the report |  |  | Configuration
|  |  | Json file configurations for template |  |  | Configuration
|  |  | Dev testing |  |  | Development
|  |  | Test server deployment |  |  | Deployment
|  |  | QA testing |  |  | QA testing
|  |  | Tags configuration for data sync |  |  | Configuration
|  |  | Preparing formula data sheet for the required calculations |  |  | Configuration
|  |  | Configuring formulas |  |  | Configuration
|  |  | Discuss an approach to create a configuration for rack utilization and rack summary sheets |  |  | Discussion |  |  |  |  | Last two sheets configuration
|  |  | Designing the approach(ERD) |  |  | Development
|  |  | Configuring data of utilization and rack summary |  |  | Configuration
|  |  | Json file configuration for rack utilization and rack summary sheets |  |  | Configuration
|  |  | Test server deployment |  |  | Deployment
|  |  | Generated reports verification - Yearly |  |  | QA testing
|  |  | Generated reports verification - Monthly |  |  | QA testing
|  |  | Generated reports verification - Customized date range |  |  | QA testing
|  |  | QA testing on report service |  |  | QA testing
6 | API | Downlaoding reports for annualy, monthly and customized time periods | Discuss about the approach |  |  | Discussion
|  |  | Finalizing the end points |  |  | Discussion |  |  |  |  | 2 end points
|  |  | Designing the approach(flow diagrams, class diagrams,ERD) |  |  | Development
|  |  | Finalizing the design |  |  | Discussion
|  |  | Integrate the report module |  |  | Development
|  |  | Implementation |  |  | Development
|  |  | Implement unit testings |  |  | Development
|  |  | Dev testing |  |  | Development
|  |  | Test server deployment |  |  | Deployment
|  |  | QA testing |  |  | QA testing
7 | GUI | Downlaoding reports for annualy, monthly and customized time periods | Discuss about the approach |  |  | Discussion
|  |  | Designing the approach(UI sketches, class diagrams) |  |  | Development
|  |  | Finalizing the design |  |  | Discussion
|  |  | Implement service |  |  | Development
|  |  | Implement UIs |  |  | Development
|  |  | Implement unit testings |  |  | Development
|  |  | Implement functions to call service and UI integration |  |  | Development
|  |  | Dev testing |  |  | Development
|  |  | Test server deployment |  |  | Development
|  |  | QA testing |  |  | QA testing
8 |  | Documentation | User Manual |  | Madushani/Kalhari
|  |  | UAT |  | Madushani/Kalhari