## Sheet1
Work plan for power optimization reports
1 story point = 2 hrs
No | Module | Main Task | Sub Tasks | Dev | QA | Type of the work | Start Date | End Date | Estimated Story Points | Target Release Date | Remarks
1 | Formula Service | Integrating peak of peak/ bug fixings changes to Formula Service latest version | Get KT about the change | Chiran/Dilini |  | KT |  |  | 1
|  |  | Get KT on data patching | Nadeeka/Dilini |  | KT |  |  | 1
|  |  | Studying the code functionalities | Dilini |  | R&D |  |  | 2
|  |  | Integrating peak off peak/ bug fixing changes | Dilini |  | Development |  |  | 4
|  |  | Dev testing | Dilini |  | Dev Testing |  |  | 2
|  |  | Test server deployment | Dilini |  | Deployment |  |  | 2
|  |  | QA testing |  | Madushani | QA testing |  |  | 5 | 12
2 | Data sync service | Integrating performance enhancment | Get KT about the change(Performance enhancement) | Nadeeka |  | KT |  |  | 3
|  |  | Studying the code functionalities | Dilini |  | R&D |  |  | 2
|  |  | Integrating performance enhancment | Dilini |  | Development |  |  | 8
|  |  | Dev testing | Dilini |  | Dev Testing |  |  | 3
|  |  | Test server deployment | Dilini |  | Deployment |  |  | 2
|  |  | QA testing |  | Madushani | QA testing |  |  | 4 | 18
3 | Formula Service | Applying a mechanism to validate minus consumptions | Discuss about scenarios that produce minus consumptions | Kalhari/Lahiru/Gayashan |  | Discussion |  |  | 2
|  |  | Discussion to finalize the mechanism to handle the scenarios that produce minus cosnumptions | Kalhari/Lahiru/Gayashan |  | Discussion |  |  | 4
|  |  | Discussing and KT and how to apply the approach to service | Kalhari/Lahiru |  | KT/Discussion |  |  | 4
|  |  | Designing the approach(flow diagrams, class diagrams) | Kalhari/Lahiru |  | Development |  |  | 4
|  |  | Finalizing the design | Lahiru |  | Discussion |  |  | 4
|  |  | Implementation | Lahiru |  | Development |  |  | 12
|  |  | Implement Unit testing | Lahiru |  | Development |  |  | 6
|  |  | Dev testing | Lahiru |  | Development |  |  | 6
|  |  | Test server deployment | Lahiru |  | Deployment |  |  | 2
|  |  | QA testing |  | Madushani | QA testing |  |  | 6 | 44
4 | Report Module | Implement a feature to apply function for data series for custom time ranges | Discuss about the approach | Hasintha/Kalhari |  | Discussion |  |  | 2
|  |  | KT on how to apply the approach to code | Hasintha/Ravihansa |  | KT/Discussion |  |  | 4
|  |  | Designing the approach(flow diagrams, class diagrams) | Ravihansa |  | Development |  |  | 3.5
|  |  | Finalizing the design | Ravihansa |  | Discussion |  |  | 3
|  |  | Implementation | Ravihansa |  | Development |  |  | 16
|  |  | Preparing sample json file and template | Dilini |  | Development |  |  | 3
|  |  | Dev testing | Ravihansa |  | Development |  |  | 3
|  |  | Test server deployment | Ravihansa |  | Deployment |  |  | 2
|  |  | QA testing (Console App) |  | Madushani | QA testing |  |  | 8 | 36.5 | 33.5
5 | Reporting Service | Implement a service to generate reports periodicaly | KT on schedule service | Kalhari |  | KT/Discussion |  |  | 2
|  |  | Studying the code functionalities | Ravihansa |  | Discussion |  |  | 2
|  |  | Integrating schedule service report project and other projects to solution of API | Ravihari |  | Development |  |  | 2
|  |  | Resolving issues during code compiling | Ravihari |  | Development |  |  | 2
|  |  | Modifying code for the changes | Ravihansa |  | Development |  |  | 4
|  |  | Preparing template for the report | Lahiru |  | Configuration |  |  | 1
|  |  | Json file configurations for template | Ravihansa |  | Configuration |  |  | 16
|  |  | Sql database configurations data sources mapping | Lahiru |  | Configuration |  |  | 3
|  |  | Dev testing | Ravihansa |  | Development |  |  | 2
|  |  | Test server deployment | Ravihansa |  | Deployment |  |  | 2
|  |  | QA testing |  | Madushani | QA testing |  |  | 8 | 36 | 28
|  |  | Tags configuration for data sync | Dilini |  | Configuration |  |  | 1
|  |  | Preparing formula data sheet for the required calculations | Dilini |  | Configuration |  |  | 1
|  |  | Configuring formulas | Dilini |  | Configuration |  |  | 1
|  |  | Discuss an approach to create a configuration for rack utilization and rack summary sheets | Dilini |  | Discussion |  |  | 1 |  | Last two sheets configuration
|  |  | Designing the approach(ERD) | Dilini |  | Development |  |  | 1
|  |  | Configuring data of utilization and rack summary | Dilini |  | Configuration |  |  | 1
|  |  | Json file configuration for rack utilization and rack summary sheets | Dilini |  | Configuration |  |  | 2
|  |  | Test server deployment | Dilini |  | Deployment |  |  | 1 | 9
|  |  | Generated reports verification - Yearly |  | Madushani | QA testing |  |  | 2
|  |  | Generated reports verification - Monthly |  | Madushani | QA testing |  |  | 4
|  |  | Generated reports verification - Customized date range |  | Madushani | QA testing |  |  | 4
6 | API | Downlaoding reports for annualy, monthly and customized time periods | Discuss about the approach | Ravihari |  | Discussion |  |  | 2
|  |  | Finalizing the end points | Ravihari |  | Discussion |  |  | 1 |  | 2 end points
|  |  | Designing the approach(flow diagrams, class diagrams,ERD) | Ravihari |  | Development |  |  | 2
|  |  | Finalizing the design | Ravihari |  | Discussion |  |  | 2
|  |  | Integrate the report module | Ravihari |  | Development |  |  | 1
|  |  | Implementation | Ravihari |  | Development |  |  | 4
|  |  | Implement unit testings | Ravihari |  | Development |  |  | 4
|  |  | Dev testing | Ravihari |  | Development |  |  | 2
|  |  | Test server deployment | Ravihari |  | Deployment |  |  | 1
|  |  | QA testing |  | Madushani | QA testing |  |  | 6 | 19
7 | GUI | Downlaoding reports for annualy, monthly and customized time periods | Discuss about the approach | Ravihari |  | Discussion |  |  | 1
|  |  | Designing the approach(UI sketches, class diagrams) | Ravihari |  | Development |  |  | 2
|  |  | Finalizing the design | Ravihari |  | Discussion |  |  | 2
|  |  | Implement service | Ravihari |  | Development |  |  | 3
|  |  | Implement UIs | Ravihari |  | Development |  |  | 2
|  |  | Implement unit testings | Ravihari |  | Development |  |  | 4
|  |  | Implement functions to call service and UI integration | Ravihari |  | Development |  |  | 3
|  |  | Dev testing | Ravihari |  | Development |  |  | 2
|  |  | Test server deployment | Ravihari |  | Development |  |  | 1
|  |  | QA testing |  | Madushani | QA testing |  |  | 6 | 20
8 |  | Documentation | User Manual |  | Madushani/Kalhari |  |  |  | 4
|  |  | UAT |  | Madushani/Kalhari |  |  |  | 4
9 |  | Overall integration testing |  |  | Madushani |  |  |  | 6
10 |  | Production deployment | Deploying all modules | Lahiru/Dilini/Ravihansa/Ravihari |  |  |  |  | 4
|  |  | Smoke testing/Verifications |  | Madushani |  |  |  | 4